## Sprint 1
Priority | Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
1 | Myles Debro | Make required fields for Sign In page | 2 | 0 | 0 | 0 | 0
1 | Jacob Baker | Complete Account Page | 4 | 4 | 5 | 0 | 0
3 | Jacob Baker | Implement Separate Account Editing View | 4 | 4 | 0 | 0 | 0
1 | Jacob Baker | Complete adding freelancers to Category Page | 4 | 0 | 0 | 0 | 0
1 | Kate Anglin | Create Freelancers data | 5 | 1 | 0 | 0 | 0
0 | Kate Anglin | Implement Freelancers and Bind together Server to Backend | 4 | 4 | 2 | 1 | 0
3 | Kate Anglin and Jab | Implement filtering skills on Category Page | 4 | 4 | 4 | 4 | 0
3 | Alec Neal (Myles) | Add Remove user from DMs | 3 | 3 | 3 | 0 | 0
2 | Alec Neal | Initialize server to function with Client (structure, class, click run and should start a local server) | 7 | 5 | 3 | 0 | 0
2 | Alec Neal | Make Dms work through server | 7 | 7 | 0 | 0 | 0
2 | Myles Debro (Alec) | Make loggin and create account work through server | 6 | 6 | 0 | 0 | 0
2 | Kate Anglin and Jab | Add More Categories to Freelancer (Add Other Option) | 3 | 3 | 2 | 2 | 0
1 | Jacob Baker | Categories page call for freelancers and show (more than 24 hard coded currently) | 4 | 0 | 0 | 0 | 0
2 | Jacob Baker | Add Hyre function UI and binding | 3 | 3 | 3 | 3 | 0
3 | Alec Neal | Make Hyre button call open a dm chat with another user | 4 | 4 | 4 | 4 | 0
3 | Myles Debro | Binds Users when creating/editing account to personal data and save in server(make it callable) | 3 | 3 | 3 | 3 | 0
3 | Myles Debro | Delete Users when editing account and save in server(make it callable) | 3 | 3 | 3 | 3 | 0
|  | Estimate Totals | 70 | 54 | 32 | 20 | 0
| Task Manager / Dev | Task Description | Hours Worked | Rounded to
Nearest half hour
| Kate Anglin | Create Freelancers data | 5 |  | Unique Names | Hours worked
| Jacob Baker | Added freelancers to Category UI, allowing the viewer to see the names as buttons. | 3 |  | Kate Anglin | 39
| Jacob Baker | Added the binding of next/previous to the page allowing you to see more than the predetermined 24 button count | 3 |  | Jacob Baker | 37.5
| Myles Debro | Make required fields for Sign In page | 2.5 |  | Myles Debro | 15
| Myles Debro | Implement deleting chats | 5.5 |  | Alec Neal | 29.5
| Jacob Baker | Implmented Account page/seperated the viewing or editing (struggled with server since merged in main with errors) | 6
| Kate Anglin | Added freelancer to Server, started implementation of the roster server-side | 2
| Kate Anglin | Completed FreelanceRoster on the server and TESTED | 3
| Kate Anglin | Started working on getting the server to communicate with the client for the freelancers | 3
| Kate Anglin | Updated Freelancer Class and still working on client server got the AddFreelancer to work but the getFreelancers doesnt | 8
| Jacob Baker | Implemeting more of Account page.. the relised we cant even make a user into a Freelancer yet | 3
| Jacob Baker | Implmenting/messing with ways to turn someone into a freelancer and not only appear as a user now | 4
| Kate Anglin | Completed deleteing a freelancer from the server | 2
| Jacob Baker | Finished implmenting the switch between user and freelancer and cleaning account page view | 4
| Jacob Baker | fixed merge conflicts and fixed some minor issues that occured | 2
| Kate Anglin | Fixed alecs bug for disabling the hyre button | 1
| Jacob Baker | Implement About page function and also fix major checkstyle errors | 3
| Kate Anglin | EXTREME programming figuring out account page data to server data implementation | 5
| Jacob Baker | EXTREME programming figuring out account page data to server data implementation | 5
| Myles Debro | Delete User from Server | 4
| Kate Anglin | Added categories to the server and can now get them from the server | 4
| Jacob Baker | Created new Filter UI on Categories page | 0.5
| Jacob Baker | CreatedUI for the Adding Categories feature, added in the view calls once clicked to add, and then fixed merge conficts | 4
| Kate Anglin | Fixed Categories Bug and some testing issues | 2
| Myles Debro | Save User bio in Server | 3
| Kate Anglin | Finished implementation of searching freelancers | 4
| Alec Neal | Created full codebase for python server and java server communication | 12
| Alec Neal | Added and fixed all test for 100% code coverage in java and python | 3
| Alec Neal | Refactored java model classes and tests to fit server communnication | 2
| Alec Neal | Added personal user DM list in python backend | 2
| Alec Neal | Fully implemented Direct Messaging to go through the server | 4
| Alec Neal | Implmented Hyre button to DM freelancer | 1.5
| Alec Neal | Reimplemented ZMQ | 1
| Alec Neal | Fixed bugs in my and others code | 3
| Alec Neal | Polished communication protocol.txt | 1
|  | Estimate Totals | 121