## Sprint 1
Priority | Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  |  | Week 1 | Week 2 | Week 3
3 | Jacob Baker | Make freelancer view page | 3 | 0 | 0 | 0
3 | Myles Debro | Add support for viewing and setting star rating on freelancer view page | 2 | 2 | 2 | 0
3 | Myles Debro | add support for storing star rating server side | 2 | 0 | 0 | 0
3 | Kate Anglin | Update categories page to allow selecting category | 1 | 0 | 0 | 0
3 | Kate Anglin | Update categories page to allow selecting multiple skills | 4 | 3 | 0 | 0
3 | Jacob Baker | Add support for freelancer view page back to categories page | 2 | 1 | 0 | 0
3 | Alec Neal | Add warning for deleting chat | 1 | 0 | 0 | 0
3 | Alec Neal | Update delete chat to only remove chat message for the user selecting delete | 1 | 0 | 0 | 0
3 | Alec Neal | if no user can view messages actually delete messages from server | 1 | 0 | 0 | 0
3 | Alec Neal | Refresh messages btn | 1 | 0 | 0 | 0
|  | Estimate Totals | 18 | 6 | 2 | 0
| Task Manager / Dev | Task Description | Hours Worked | Rounded to
Nearest half hour
| Jacob Baker | Seperated the freelancer view page from the Account and fixed all issues. Also managed checkstyle issues. | 4 |  | Unique Names | Hours worked
| Jacob Baker | Added the back button UI and some simple data place holders. | 1 |  | Jacob Baker | 10
| Jacob Baker | Made the back button work for the category page | 1 |  | Alec Neal | 11
| Jacob Baker | Tested all of the view model class created to keep 100% coverage in the class | 2 |  | Kate Anglin | 8.5
| Alec Neal | Added refresh button for DMs | 1 |  | Myles Debro | 9
| Alec Neal | Fixed bugs in server and Client | 1 |  | 0
| Kate Anglin | Updated the Categories page to allow the selection of a category and selecting skills | 2
| Kate Anglin | Completed category selection | 1
| Alec Neal | Created confirmation pop up when removing user from contact list. | 1
| Alec Neal | Implmented contact list to only remove a user from personal contact list and not both | 0.5
| Alec Neal | Implemented deletion of message log if neither user can message the other | 2
| Alec Neal | Added tests and fix UI bugs in the DM page | 1
| Myles Debro | Add support for storing star rating server side | 2
| Kate Anglin | Completed Skill selection | 5
| Jacob Baker | Finished the data storing for back button now works as intended. | 2
| Kate Anglin | Stopped updating freelancers when a skill is selected/deslected | 0.5
| Myles Debro | Add support for star ratings client side | 7
| Alec Neal | Fixed bug for myles | 0.5
| Alec Neal | Fixed multiple UI bugs in DM view | 2
| Alec Neal | Updated Class Diagram and communication protocol | 2
|  | Estimate Totals | 38.5
Documentation
Complete? | Name | Task Description
TRUE | Alec Neal | Update Class Diagram
TRUE | Alec Neal | Check Testing and either notfiy the creator for this sprint or fix non upto date ones from last sprint
TRUE | Myles Debro | Use Senerio for Sign In to Existing Account.txt
TRUE | Myles Debro | Use Senerio for Communicate With Other Users.txt
TRUE | Myles Debro | Use Senerio for Review Freelancer.txt
TRUE | Kate Anglin | Updated ReadMe for selecting skills
TRUE | Kate Anglin | Updated Product Backlog
TRUE | Kate Anglin | Use Senerio for Search for Freelancers Based on Criteria.txt
TRUE | Kate Anglin | Use Senerio for View Categories of Freelancers.txt
TRUE | Kate Anglin | Use Senerio for Hire a Freelancer.txt
TRUE | Jacob Baker | Use Senerio for Create and View Account.txt
TRUE | Jacob Baker | Use Senerio for Become a Freelancer and Edit Account.txt
TRUE | Jacob Baker | Use Senerio for Post Freelancer Job Skills.txt
TRUE | Jacob Baker | Use case diagram
TRUE | Jacob Baker | Add Burndown to github