## Sprint 1
Task Manager / Dev | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Jacob Baker | Initalize Project | 1.5 | 0 | 0 | 0 | 0
Jacob Baker | Implment Login Screen UI | 2.5 | 0.5 | 0.5 | 0.5 | 0
Jacob Baker | Implment Home Screen UI (Signed in and out) | 4 | 0.5 | 0.5 | 0.5 | 0
Jacob Baker | Implment Category Pull Down UI (People showing) | 2 | 2 | 2 | 0.5 | 0
Jacob Baker | Implment the Category's People view UI | 2 | 2 | 2 | 0.5 | 0.5
Jacob Baker | Implment Acount Pages UI (Freelance vs employer) | 3 | 1.5 | 0.5 | 0.5 | 0.5
Jacob Baker | Implment DM UI | 4 | 4 | 0.5 | 0.5 | 0.5
Jacob Baker | Implment Create Account UI | 4 | 0.5 | 0.5 | 0.5 | 0
Myles Debro | Implment UI binding | 8 | 2 | 0.5 | 2 | 1
Alec Neal | Implment Storing messages (Corley says List) | 11 | 6 | 6 | 6 | 6
Myles Debro | Implment Login feature (admin login idea) | 3 | 0 | 2 | 1 | 3
Myles Debro | Implment Logout feature | 3 | 0 | 0 | 2 | 0.5
Alec Neal | Create Account (Save to doc for now) | 6 | 2 | 2 | 2 | 2
Kate Anglin | Implment abilbity to create account bio | 4 | 4 | 2 | 2 | 0
Alec Neal | Implment Storing account bio info (maybe text doc for now) | 5 | 1 | 1 | 1 | 1
Kate Anglin | Implment edit personal account bio | 3 | 3 | 2 | 2 | 0
Kate Anglin | Implment viewing other account bio's | 4 | 4 | 4 | 4 | 4
Jacob Baker | Implment Search and Filter UI | 2 | 2 | 2 | 0.5 | 0.5
Kate Anglin | Implement Search and Filters backend | 6 | 6 | 6 | 3 | 0
Kate Anglin | Implement Categories | 3 | 0 | 0 | 0 | 0
| Estimate Totals | 81 | 41 | 34 | 29 | 19.5
Task Manager / Dev | Task Description | Initial Estimate | Rounded to
Nearest half hour
Jacob Baker | Initalized project as a starter project with a start method able to open window | 0.5
Jacob Baker | Implemented the UI for the Home Screen while signed out | 2
Jacob Baker | Finalized HomePage Ui with some missing features and made sure to handle on click | 1
Jacob Baker | created 2 sign in / create account pages for feed back at next meet | 1.5
Jacob Baker | created account page with minimal data provided | 1
Jacob Baker | tinkering with account page | 2
Kate Anglin | created simple User Class | 1.5
Kate Anglin | Implement Categories | 1.5
Alec Neal | Created better User Class (sorry kate) | 2
Alec Neal | Created direct message handler | 1
Alec Neal | Created temporary server actor | 2
Alec Neal | Created messge class for future dm storage | 0.5
Kate Anglin | Created an even better User Class (sorry alec) | 1.5
Kate Anglin | Created Freelancer Class | 3.5
Jacob Baker | Finalized Direct Messages Ui with some missing features | 4
Jacob Baker | Finalized the Account page | 1
Kate Anglin | Sorting Freelancers by Category | 4
Jacob Baker | Implmented the Category Page UI and added filter combo box | 3.5
Jacob Baker | Implmented the drop down to view other categories in the UI | 2
Kate Anglin | Implement Filtering Categories Backend | 2
Kate Anglin | Implemented edit personal account bio | 2
Jacob Baker | Implmented and Binded All of the Category and Category Pull Down and Fixed several errors. | 7
| Estimate Totals | 47